## Light
E-commerce Website
Agile Project Group 3 |  |  |  |  | Legend: |  |  | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Katherine Mulder and Shaniece Eagan
Project Start Date: | 2022-02-15 | [6 empty] | February | [13 empty] | March | [34 empty] | April
Scrolling Increment: | 1 | time axis 2022-02-16 to 2022-04-12
Milestone description | Category | Assigned to | Progress | Start | Days | End | Completed by | time axis 2022-02-16 to 2022-04-12
ITERATION 1
Iteration planning and meeting | Milestone | All Member | 100% | 2022-02-15 | 1 | 15/02/2022 | All Member
Complete stakeholder register | Goal | Shaniece | 100% | 2022-02-28 | 5 | 05/03/2022 | Shaniece | 2022-02-28: 2; 2022-03-01: 2; 2022-03-02: 2; 2022-03-03: 2; 2022-03-04: 2
Design persona | Milestone | Katherine | 100% | 2022-02-16 | 2 | 18/02/2022 | Katherine | bar: 2022-02-16 to 2022-02-17
Review and test persona | Milestone | Shaniece | 100% | 2022-02-20 | 1 | 21/02/2022 | Shaniece | bar: 2022-02-20
Complete all tasks in the iteration 01 | Goal | All Member | 100% | 2022-03-10 | 10 | 20/03/2022 | All Member | 2022-03-10: 2; 2022-03-11: 2; 2022-03-12: 2; 2022-03-13: 2; 2022-03-14: 2; 2022-03-15: 2; 2022-03-16: 2; 2022-03-17: 2; 2022-03-18: 2; 2022-03-19: 2
Submit progress report | Milestone | Katherine | 100% | 2022-03-14 | 12 | 26/03/2022 | Katherine
ITERATION 2
Iteration planning and meeting and review of last meeting actions | Milestone | All Member | 100% | 2022-03-29 | 1 | 29/03/2022 | All Member | bar: 2022-03-29
Create a Repository on GitHub Boards and work on setting up GitHub | Milestone | Katherine | 100% | 2022-03-30 | 3 | 02/04/2022 | Katherine | bar: 2022-03-30 to 2022-04-01
Complete resource needs report | Goal | Katherine | 100% | 2022-04-04 | 6 | 10/04/2022 | Katherine | 2022-04-04: 2; 2022-04-05: 2; 2022-04-06: 2; 2022-04-07: 2; 2022-04-08: 2; 2022-04-09: 2
Review and test the resource needs report | Goal | Shaniece | 100% | 2022-04-08 | 2 | 10/04/2022 | Shaniece | 2022-04-08: 2; 2022-04-09: 2
Create and update Gantt chart | Milestone | All Member | 100% | 2022-03-25 | 4 | 29/03/2022 | All Member
Complete all tasks in the iteration 02 | Goal | All Member | 100% | 2022-04-29 | 16 | 15/05/2022 | All Member
Submit progress report | Milestone | Shaniece | 100% | 2022-04-05 | 17 | 22/04/2022 | Shaniece | bar: 2022-04-05 to 2022-04-12
ITERATION 3
Iteration planning and meeting and review of last meeting actions | Milestone | All Member | 100% | 2022-04-29 | 1 | 29/04/2022 | All Member
Risk register | Goal | Katherine | 100% | 2022-05-12 | 3 | 15/05/2022 | Katherine
Edit wiki pages and work on design GitHub board | Milestone | Katherine | 100% | 2022-05-18 | 2 | 20/05/2022 | Katherine
Integration and publish website | Goal | All Member | 100% | 2022-05-20 | 1 | 21/05/2022 | All Member
User acceptance testing | Milestone | Shaniece | 100% | 2022-05-24 | 2 | 26/05/2022 | Shaniece
Complete all tasks in the iteration 03 | Goal | All Member | 100% | 2022-05-29 | 15 | 13/06/2022 | All Member
Submit progress report | Milestone | All Member | 100% | 2022-05-19 | 16 | 06/06/2022 | All Member